## Bug Report
Bug ID | Severity | Component | Summary | Test | Scene | To reproduce | Expected outcome | Actual outcome | Screenshot | Date
1 | 2 Critical Bug | Player Movement | Player would fall of some of the levels edges | 3 | General Test Scene | Walk to the edge directly to the right of the of the player when spawning in | Player should just hit the imaginary barrier and not fall off. | Player falls off the edge of the map | N/A | 2023-11-02
2 | 2 Critical Bug | Player Movement + player kicking | Sometimes after kicking, the player would rotate and move uncontrollably | 6 | General Test Scene | Kick the ball around in the general test scene, particularly around slopes. | Should return to moving normally after kicking | Player moves and rotates weirdly with no way of stopping it | N/A | 2023-11-07
3 | 3 Minor Bug | Camera | Camera wouldn't look at the player instead was at player level | Testing level 1 | Level 1 | Play Level 1 | Camera should look at player and follow from 45 degree angle. | Camera was directly on top of player and wasn't showing the world correctly. | N/A | 2023-11-07
4 | 2 Critical Bug | Goal + Ball | When goal is scored, the level does not change. | Testing level 1 | Level 1 | Use the player to kick the ball through the hoop and see what happens. | Should Automatically move to Level 2. | Nothing happens, the ball just goes through the hoop. | N/A | 2023-11-09
5 | 3 Minor Bug | UI kick counter | Kick counter increments whenever space is pressed rather than when an actual kick occurs. | 14 | General Test Scene | Press spacebar multiple times and watch the kick counter. | The kick counter should only increment after an actual kick occurs not just when space is pressed. | The kick counter increments everytime space is pressed. | N/A | 2023-11-09
7 | 2 Critical Bug | Player movement + Kicking | After kicking Player gets stuck facing diagonal and cant move. | Testing level 3 | level 3 | Go next to the ball, grab the ball, kick the ball. | The ball should be grabbed, then kicked, after kicking player should be able to move as per usual. | Ball is grabbed and kicked however player gets stuck in a weird position and cannot move. | Bug7.jpg | 2023-11-09
8 | 3 Minor Bug | Player Movement | Player falling through the world blocks | Testing level 1 | level 1 | Go to the very back corner of the map and keep running into it, player can glitch through the map | Player should hit the wall and just stay within the map. | Player gltiches through the floor and walls and falls through the map | bug8.jpg | 2023-11-09
9

## QA Plan
Test ID | Requirements | Test Scene | Task | Expected result
1 | 3b & 3c & 3d | Move Test Scene | Start the Scene, Press each key listed below and check that the corresponding movement is achieved. W - moves player up A - moves player left S - moves player down D - moves player right A & W - moves player Diagonally up/left D & W - moves player Diagonally up/right A & S - moves player Diagonally down/left D & S - moves player Diagonally down/right After this, repeat above but holding shift and compare move speed to when not holding shift. Once that is completed, repeat above again but observe the rotation of the player when changing the direction. | Player should correctly move either up,down,left,right and diagonally, when shift is held player should move faster in each direction than when not holding down shift. When the direction changes, the player should turn smoothly to face the way its moving rather than instantly.
2 | 3e & 3f | Move Test Scene | Start the Move Test Scene. Using WASD, move the player up a slope, then back down once you reach the top. Do this for each of the slopes located to the side of the Scene. While doing this, observe whether the player moves off the ground. Also observe the speed which the player moves. | Player should move up and down each slope without any issues. The player speed should not change and the player should remain attached to the ground while moving.
3 | 3g & 3h | Move Test Scene | Start the Move Test Scene. Using WASD, move to each side as well as corner of the map and see whether the player falls off. After completing this, move to the edge of the cliff and observe whether the player falls off. | Player should reach the edge of the map and stop without falling off the edge. Player should reach the edge of the cliff and not fall off it.
4 | 3i | Move Test Scene | Start the Move Test Scene. Using WASD, move towards and collide into the Tree obstacle and observe whether it moves smoothly, whether it goes through it, glitches around it or any other buggy behaviour. Using WASD, then move towards and collide into the Barrier obstacle and observe whether it moves smoothly, whether it goes through it, glitches around it or any other buggy behaviour. Using WASD, then move towards and collide into the Rocks obstacle and observe whether it moves smoothly, whether it goes through it, glitches around it or any other buggy behaviour. | Player should bump into each obstacle, either being stopped by it or moving around its perimeter without going through it or glitching out.
5 | 2a & 2b | Ball Test Scene | Start the Ball Test Scene Move the player and collide into the ball which is to the right of the map. Observe the movement and collide into it again. Repeat this a few times and see how it acts, whether its bouncy and responds to being run into. Also use the player to push the ball to each edge of the map, seeing if it clips through or not. | Each time the player hits the ball, it should react in a fairly natural way to a beach ball. It should move around when bumped by the player (aka the player shouldn’t move through the ball). The ball should just simply bounce back or sit on the edge when pushed to the sides of the map.
6 | 4a & 4b | Ball Test Scene | Start the Ball Test Scene Hold "Spacebar" and see whether the player can move while holding it and whether the player changes to enter a "grabbing state". Let go of spacebar and see if you can move. Move to be next to the ball using WASD and hold spacebar again. Observe whether the ball is picked up by the player and it hovers in front of the player. Release spacebar and observe. | When the spacebar is initially held, player shouldn’t be able to move and the ball shouldn't be picked up by the player. Player should be able to move freely once spacebar is released. After moving next to the ball, pressing space should move the ball to hover in front of the player and when released the ball should shoot out in the direction the player is facing. After this the player should be able to move again.
7 | 4c & 4d &4e | Ball Test Scene | Start the Ball Test Scene Move to be next to the ball using WASD and hold spacebar While holding space, see if there is a trajectory being drawn. Still while holding space, hold each key until it stops moving in that direction: Hold the W key to see if the aiming moves down. Hold the S key to see if the aiming moves up. Hold the A key to see if the aiming moves left. Hold the D key to see if the aiming moves right. Once each direction is tested, let go of the spacebar and observe if the ball is launched in the given direction. | The ball should be grabbed and the kick trajectory portrayed. It should move in the corresponding direction until it reaches its limit (it should stop moving at some point and not do a full 360). This should work for each direction, then when space is released the ball should fly in that direction by its specified impulse.
8 | 5b | Goal test scene | Start the Goal Test Scene Hold spacebar, use WASD to aim a kick straight into the goal's ring. Let go of spacebar and see what happens, particularly the player and any UI, when the ball goes through the ring. If the ball misses the ring, retry the test scene. | The ball should correctly be picked up and kicked through the ring, when the ball passes through the ring it should wait a few seconds, while waiting the player animation should change to play the cheer animation, then a UI box should appear.
9 | 6a & 6b & 6c | Move Test Scene | Start the Scene, Stand still for 5 seconds and observe the player's character, more specifcially, whether it's animated or not. Then Hold each key listed below for 2 seconds and check that the corresponding animation is achieved. W - walk animation A - walk animation S - walk animation D - walk animation After that hold the shift key as well as each key listed below for 2 seconds and check that the corresponding animation is achieved. W - sprint animation A - sprint animation S - sprint animation D - sprint animation Observe each key and note whether they are animated or not. | The character should first play the idle animation while not moving. Then it should play the walk animation for each key listed and the player should appear to be walking. Same should occue while holding the sprint button, it should play the sprint animation and the player should appear to be sprinting.
10 | 6d & 6e | Ball Test Scene | Start the Ball Test Scene Move to be next to the ball using WASD and hold spacebar When the ball is picked up by the player, observe the animation of the player. Then release the spacebar. When spacebar is released also observe the animation of the player. | When the ball is initially picked up, the interact animation should play on the player. When space is released and the ball is kicked, the throwing animation should play on the player.
11 | 7b & 7c | Move Test Scene | Start the Move Test Scene Observe the angle that the camera is viewing the scene from. Then use WASD to move the character and observe whether the player stays in the center of the screen. | The camera should look at the scene from a 45 degree angle, and the player should stay in the center of the screen when moving.
12 | 7d & 7e & 7f | Ball Test Scene | Start the Ball Test Scene Don't move and see if there's an arrow to the right of the screen pointing towards the ball. Then move to be next to the ball using WASD and then hold spacebar to start a kick. When the ball is picked up by the player, observe the camera movement. Then release the spacebar. When spacebar is released and the ball is kicked observe the camera movement. | There should be an arrow pointing towards the ball on the right of the screen which dissapears when the ball becomes visible. When holding the ball the camera should smoothly transition to show more of the world in the direction the kick is aiming. When released, the camera should smoothly transition back to following the player.
13 | 8b | Sample Test Scene | Start the Sample Test Scene. Observe any UI that appears, observe if a box appears, if the box displays the level number, the "par" and a start button. After checking the above, press the start button. | A box should appear displaying the level number "-1", the par 2 and a start button. When the start button is pressed the box should dissapear and the level should be completely visible.
14 | 8c & 8d | Sample Test Scene | Start the Sample Test Scene. Press the start button. Move the player around the map, kicking the ball towards the goal. Every time a kick is taken, check the UI display in the top left. Get the ball and player in front of the goal and shoot it through. When the ball is shot into the goal, observe any UI that appears, particularly if it displays: - The par - The kicks taken - a total score of all levels completed - a retry button - a next button Press the retry button if there is one. This should restart the current level. Repeat all the steps above but instead press the next button, this should then load a new scene with a reset kick counter. | Every time a kick is made, the kick counter in the top left of the screen should increment. When the goal is scored, a UI should pop up showing the levels Par, the kicks taken, and a total score. It should also have two buttons, when the reset button is pressed it should restart the current level as well as the kick counter. When the next button is pressed, it should load a new scene, where the kick counter will be reset and the par displayed at the start.
15 | 5b | Level 1 | Start Level 1. Using WASD as well as the spacebar, move the player and ball around the map untill you are in front of the goal. Shoot the ball through the goal. See if the final UI appears and the level changes. | Once the ball travels through the goal, the final UI box should appear allowing for retry or next level, when next is pressed level 2 should load in. Associated Bug : Bug 4
16 |  | Level 3 | Start Level 3. Using WASD to walk up to the ball. Hold spacebar so that the ball is grabbed by the player. Release the spacebar and kick the ball. Use WASD to move around and see movement works. | Player should grab the ball and it should hover in front of the player, the player should then release the ball and still be able to move afterwards as per normal. (Player shouldn’t get stuck in the kicking mode and not be able to move) Associated Bug : Bug 7
17 | 3g | Level 1 | Start Level 1. Using WASD move the player up the ramp then run into the very back corner of the map (see screenshot in bug 8 for reference) Collide back and forth into this corner 5-10 times and check if player falls through the world. | Player should just bounce off the wall each time and not glitch through the wall or floor falling endlessly. Associated Bug: bug 8